## INSTRUCTIONS
The ARPA team provides updates to the Interim Finance Committee (IFC) at every meeting. Subrecipient Spend Plan updates are included in the report. Please provide updates by the deadline below: |  |  |  | IFC: | 2026-04-16
|  |  |  | DEADLINE: |  | All funds must be spent by: | 2026-12-31
|  |  |  | COUNTDOWN (from IFC): |  | 8 months 15 days
|  | Spend Plan updates due for April IFC: | 2026-04-16
|  | Spend Plans are due by COB: | 2026-03-25
ARPA SUBRECIPIENT - SPEND PLAN UPDATE INSTRUCTIONS:
Complete Spend Plan based on applicable months remaining for each project period, allocating the UNSPENT BALANCE REMAINING.
The Total Reimbursements (Column AE) is based on RFR submittals received into the COVID Mailbox through 3/16/26.
Column AH is for any pending RFRs that have NOT been submitted to ARPA through February 2026.
Columns AI through AV are for projections from March 2026 through the Project End Date.
Column AW is the check totals, which cannot exceed the unspent balance.
Complete the Status and Comments columns.
The expectation is to complete monthly amounts based on the project expenditure timelines for reimbursements using spending trends, spending cycles and/or knowledge of ramping up expenditures.
Any amounts identified as spend plan savings/deobligations must be accompanied by a deobligating ACR with the accompanying work program due MARCH 30, 2026. This allows GFO to reallocate funding immediately.
Now is the time to Identify any delays and/or concerns about spending the balance remaining by your Project End Date.
Plan for April 2026 IFC to be available for questions regarding your projects.
Send your responses to covid19@finance.nv.gov
For any questions, please reach out to Lesa Galloway, lgalloway@finance.nv.gov .

## ARPA PROJECTS-ACTIVE
[10 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 422.52 | 18904363.18 | 61698969.45 | 83046929.76 | 51621698.66 | 0 | 215272383.57
[29 empty] | RFR'S RECEIVED THROUGH 3/16/2026 |  |  | SPEND PLAN UPDATES - FOR THE REMAINDER OF THE PROJECT PERIOD
Agency Number | Agency | Allocation Number | Recipient Name | Sub Recipient | Project Description | Start Date | End Date | BA# | CAT(s) | Original NOA Amount | Supplemental Allocations NOA Amount | Amendment(s) | TOTAL REVISED ALLOCATION Original NOA + Supplemental + Amendments | SFY 22 Deobligations | SFY 23 Deobligations | SFY 24 Deobligations | SFY 25 Deobligations | SFY 26 Deobligations | SFY 27 Deobligations | Total Deobligations (CALCULATED COLUMN) | TOTAL ALLOCATION (CALCULATED COLUMN) | SFY21 Amount Spent | SFY22 Amount Spent | SFY23 Amount Spent | SFY24 Amount Spent | SFY25 Amount Spent | SFY26 Amount Spent | SFY27 Amount Spent | TOTAL REIMBURSEMENTS PAID PER RFR'S RECEIVED BY SUBRECIPIENTS | TOTAL UNSPENT BALANCE GFO PAYMENT LEDGERS | % Spent | PENDING RFR'S SUBMITTED AFTER 3/16/2026 FOR JULY-FEB | 2026-03-15 | 2026-04-14 | 2026-05-14 | 2026-06-13 | 2026-07-13 | 2026-08-12 | 2026-09-11 | 2026-10-11 | 2026-11-10 | 2026-12-10 | FINAL CLOSE-OUT | SPEND PLAN TOTAL | CK TOTALS (SPEND PLAN TOTAL CANNOT EXCEED UNSPENT BALANCE) | STATUS: *ON-TRACK *DELAYS (explain) *SAVINGS IDENTIFIED ** NO RESPONSE | SUB-RECIPIENT COMMENTS: | ck
400 | DHHS | 23EIPRC01 | DHHS- DO | N/A | EARLY INTERVENTION PERSONNEL CENTER | 2022-10-20 | 2026-06-30 | 3276 | 40 | 368100 |  |  | 368100 |  |  |  | 13339.4 |  |  | 13339.4 | 354760.6 |  |  | 16749.46 | 69421.2 | 155690.7 | 70607.26 |  | 312468.62 | 42291.98 | 88.08% | 0 | 2026-03-15: 14722.69; 2026-04-14: 11394; 2026-05-14: 9115.2; 2026-06-13: 7060.09 |  | 42291.98 | 0 | On track | This project is for BA3276, which moved to agency 402. Temporary contractor thorugh Manpower, Business Productivity Suite, and educational materials. The contractor will be compensated using the remaining project funds until those funds are fully exhausted. | 0
400 | DHHS | 23NVTRI01 | DHHS- DO | N/A | NEVADA TRANSPLANT INSTITUTE | 2022-10-20 | 2026-12-31 | 3195 | 39 | 15000000 |  |  | 15000000 | [6 empty] | 0 | 15000000 |  |  | 620663.74 | 7583393.67 | 2526979.11 | 2966485.78 |  | 13697522.3 | 1302477.7 | 91.32% | 0 | 737095.7 | 107717 | 107717 | 97717 | 97717 | 88063 | 66451 | 0 | 0 | 0 | 0 | 1302477.7 | 0 | ON-TRACK | - Preliminary site monitor was conducted on 3/5/2026. All infrastructure was observed related to the transplant ecosystem. -Donor Care Unit is expected to open April 15th. All equipment has been purchased and will be delivered once space finishings have been completed. - The Donor Transplant Testing facility is now complete and testing donors in NV. The lab is fully operational and has been surveyed by both FDA and CLIA. | 0
402 | ADSD | 23CMSMI01 | DHHS-ADSD | N/A | Case Management System Modernization/Integration | 2024-02-08 | 2026-06-30 | 3151 | 41 | 7500000 |  |  | 7500000 | [6 empty] | 0 | 7500000 |  |  | 55865 | 367393.98 | 3197831.07 | 1625153.22 |  | 5246243.27 | 2253756.73 | 69.95% | 0 | 239747.5 | 239747.5 | 249747.5 | 249747.5 | 487147.5 | 249747.5 | 232179.33 | 220347.5 | 85344.9 | 0 | 0 | 2253756.73 | 0 | On track | Note that the end date in this file was incorrect. NOA says 12/31/2026. Projection methodology: - Guidesoft Inc MSA Contractors based on monthly average through August 2026, with reduced hours for Sept.-Nov. 2026. - O365 based on monthly average costs. - Insight Public Sector based on contract deliverables. - Wellsky based on contract deliverables. | 0
402 | ADSD | 23FCWPL01 | DHHS-ADSD | N/A | Personal Care Workforce Impact | 2022-10-20 | 2026-12-31 | 3278 | 62 | 5000000 |  |  | 5000000 | 0 |  | 2000000 |  |  |  | 2000000 | 3000000 |  |  |  | 5084.56 | 360844.62 | 378689.99 |  | 744619.17 | 2255380.83 | 24.82% | 0 | 510745.71 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 82000 | 82000 | 80635.12 | 0 | 2255380.83 | 0 | On track | Projection methodology: - Public Health Supportive based on project plan. - KPS3 based on project deliverable schedule. | 0
402 | ADSD | 23HCAPD01 | DHHS-ADSD | N/A | Home/Chore Assistance for people with Disabilities | 2022-10-20 | 2026-06-30 | 3278 | 62 | 1559280 |  |  | 1559280 | 0 |  | 59280 |  |  |  | 59280 | 1500000 |  |  |  | 193311.08 | 916278.09 | 135118.2 |  | 1244707.37 | 255292.63 | 82.98% | 0 | 2026-03-15: 62000; 2026-04-14: 65000; 2026-05-14: 65000; 2026-06-13: 63292.63 |  | 255292.63 | 0 | On track | Projection methodology: - Acumen Fiscal Agent based on monthly projections for self-directed service support (Jan.-Dec. 2025 reflects approved services, monthly average used for Dec. 2025-Jun. 2026) - Washoe County based on projections for direct services, reflects the monthly average used for Dec. 2025-Feb. 2026) - Jewish Family Service Agency based on projections for monthly direct service and administrative cost (amount varies by month) | 0
402 | ADSD | 23INHSV01 | DHHS-ADSD | N/A | In home Services, home modifications, assistive tech | 2022-10-20 | 2026-12-31 | 3278 | 62 | 2090000 |  |  | 2090000 | 0 |  | 59280 |  |  |  | 59280 | 2030720 |  |  |  | 1001269.81 | 942256.53 | 63141.5 |  | 2006667.84 | 24052.16 | 98.82% | 0 | 13559 | 10493.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24052.16 | -1.4916e-10 | On track | Working with subrecipient/provider to fix RFR errors before payment. | 0
402 | ADSD | 23RFPCN01 | DHHS-ADSD | N/A | RFP Consultant for Intensive Behavioral Support Homes | 2022-10-20 | 2026-12-31 | 3279 | 34 | 14520000 |  |  | 14520000 |  |  | 2000000 |  | 1698250 |  | 3698250 | 10821750 |  |  |  | 185103.94 | 1468023.98 | 1998218.27 |  | 3651346.19 | 7170403.81 | 33.74% | 0 | 717040.38 | 717040.38 | 717040.38 | 717040.38 | 717040.38 | 717040.38 | 717040.38 | 717040.38 | 717040.38 | 717040.39 | 0 | 7170403.81 | 0 | On track | Based on our current expenditures and the understanding that we will be making additional expenditures due to Incentives being paid out to the participating providers. | 0
402 | ADSD | 23RSBEX01 | DHHS-ADSD | N/A | Residential Setting Beds Expansion | 2022-10-20 | 2026-03-31 | 3278 | 63 | 4000000 |  |  | 4000000 | [6 empty] | 0 | 4000000 |  |  |  | 127023.52 | 3144731.74 | 715680.38 |  | 3987435.64 | 12564.36 | 99.69% | 0 | 2026-03-15: 12327.68 |  | 12327.68 | -236.68 | Savings Identified | Subaward de-obligations | 0
402 | ADSD | 23SVNEX01 | DHHS-ADSD | N/A | Service Navigation Expansion | 2022-10-20 | 2026-12-31 | 3278 | 62 | 1646881 |  |  | 1646881 | 0 |  | 500000 |  |  |  | 500000 | 1146881 |  |  |  | 225000 | 478445.96 | 122062.21 |  | 825508.17 | 321372.83 | 71.98% | 0 | 50500 | 50500 | 50500 | 50500 | 20000 | 20000 | 20000 | 20000 | 20000 | 19372.83 | 0 | 321372.83 | 0 | On track | Projection methodology: - Money Management International based on monthly contract amount. - Jewish Family Service Agency, Lyon County, and Access to Healthcare Network based on remaining balance and award, split across remaining months. - KPS3 based on contract deliverables (Start date for additional deliverable in Jan. 2026, continuing through Jun. 2026.) - Nevada Public Health Foundation based on contract deliverables (Higher amount in Apr. and Jun. 2026, other months in project period at $10k.) | 0
406 | DPBH | 22BHCGM01 | DHHS-DPBH | N/A | CONTRACT MANAGEMENT SYSTEM | 2022-05-05 | 2026-06-30 | 3223 | 19 | 477606 |  |  | 477606 | [6 empty] | 0 | 477606 |  |  | 326628 | 60282 | 39664.2 | 120 |  | 426694.2 | 50911.8 | 89.34% | 0 | 2026-03-15: 12727.95; 2026-04-14: 12727.95; 2026-05-14: 12727.95; 2026-06-13: 12727.95 | 0 | 50911.8 | 0 | On Track | Project performance period extended for continued work and support of completing project tasks. System configuration updates are required for templates and documents. Some updates to functionality as well. Spend plan calculated on equal amounts for remaining months of project. | 0
406 | DPBH | 22BHSTF01b-c | DHHS-DPBH | N/A | DPBH STAFFING for ARPA Reporting-SFY24 & SFY25 | 2023-07-01 | 2027-03-31 | 3223 | 01 / 18 | 552445 | 404873 |  | 957318 | [6 empty] | 0 | 957318 |  |  |  | 249208.08 | 252955.18 | 163824.92 |  | 665988.18 | 291329.82 | 69.57% | 0 | 29132.98 | 29132.98 | 29132.98 | 29132.98 | 29132.98 | 29132.98 | 29132.98 | 29132.98 | 29132.98 | 29133 | 0 | 291329.82 | 0 | On Track | Project performance period extended for continued work and support of completing project tasks. Project on-track to fully expend all funds. Spend plan calculated on equal amounts for remaining months of project. | 0
406 | DPBH | 23CFAEP01 | DHHS-DPBH | N/A | EPIDEMIOLOGIST | 2022-10-20 | 2026-12-31 | 3219 | 34 | 5000000 |  |  | 5000000 | [6 empty] | 0 | 5000000 |  |  | 5642.56 | 191705.75 | 1410887.74 | 1002900.16 |  | 2611136.21 | 2388863.79 | 52.22% | 0 | 334381.57 | 228275.8 | 228275.8 | 228275.8 | 228275.8 | 228275.8 | 228275.8 | 228275.8 | 228275.8 | 228275.82 | 0 | 2388863.79 | 0 | On Track | UNR PhD (3), MS HAB (5), MPH Epi (3; 1 moved to Grad Special), Grad Special MPH Epi (1), Epidemiology and Biostatistics Certificate (3; 1 moved to Grad Special), Online Public Health Data Management and Analysis Certificate (3), Undergraduate Public Health (2), Graduate Assistant MS HAB (3), Graduate Assistant MPH Epi (7). UNLV Call for Applications closed for Spring 2026. Total Scholarships given in Fall 2025: 41(Undergraduate= 6; Master's= 15; Doctoral=20). | 0
406 | DPBH | 23CSSBC01 | DHHS-DPBH | N/A | CRISIS STABILIZATION CENTER | 2022-07-01 | 2026-06-30 | 3165 | 63 | 20000000 |  |  | 20000000 | 0 | 0 | 5000000 |  |  |  | 5000000 | 15000000 |  |  | 4669.1 | 10780348.58 | 3123414.75 | 0 |  | 13908432.43 | 1091567.57 | 92.72% | 0 | 2026-03-15: 1091567.56; 2026-04-14: 0; 2026-05-14: 0; 2026-06-13: 0 | 0.01 | 1091567.57 | 0 | On Track | The remaining projected balance processed with the Renown subaward, the enitre remaining balance has been expended. Project open to complete close out activities. | 0
406 | DPBH | 23EMGCS01 | DHHS-DPBH-CRISIS RESPONSE | N/A | EMERGENCY CRISIS CARE (Transfer 5 million to DCFS) | 2022-07-01 | 2026-06-30 | 3165 | 64 | 10000000 |  |  | 10000000 | 0 | 5000000 | 1900000 |  |  |  | 6900000 | 3100000 |  |  | 57796.22 | 2079879 | 698605.6 | 249285.96 |  | 3085566.78 | 14433.22 | 99.53% | 0 | 2026-03-15: 3608.31; 2026-04-14: 3608.31; 2026-05-14: 3608.31; 2026-06-13: 3608.29 | 0 | 14433.22 | 2.6193e-10 | On Track | There is remaining balance of $14,433.22. Received extension request approval, providing until 6/30/2026 to expend remaining amount giving a monthly projection of $3,608.31 x 4 Months. | 0
406 | DPBH | 23GIDTR01 | DHHS-DPBH | N/A | GENOMIC INFECTIOUS DISEASE TRACKING | 2022-10-20 | 2026-06-30 | 3219 | 35 | 1500000 |  |  | 1500000 | [6 empty] | 0 | 1500000 |  |  |  | 131435.79 | 943395.25 | 381659.96 |  | 1456491 | 43509 | 97.1% | 0 | 2026-03-15: 10877.25; 2026-04-14: 10877.25; 2026-05-14: 10877.25; 2026-06-13: 10877.25 | 0 | 43509 | 0 | On Track | Project on track to fully spend down by end of performance period. Spend plan calculated on equal amounts for remaining months of project. | 0
406 | DPBH | 23HCWSS02 | DHHS-DPBH | N/A | Health Care Workforce Scholarships (Transferred from DHCFP) | 2023-06-14 | 2026-12-31 | 3234 | 22 | 5494300 |  |  | 5494300 | [6 empty] | 0 | 5494300 |  |  |  | 201861.5 | 1819585.17 | 1618885.18 |  | 3640331.85 | 1853968.15 | 66.26% | 0 | 184829.28 | 185459.88 | 185459.88 | 185459.88 | 185459.88 | 185459.88 | 185459.88 | 185459.88 | 185459.88 | 185459.83 | 0 | 1853968.15 | 0 | On Track | Healthy Communities Coalition 22 scholarship recipients. 20 CHW I, 2 CHW II certifications. 100% spent down. UNR Larson Institute 20 scholarship recipients CHW, 15 English Doula, 17 Spanish Doula scholarship recipients, 20 scholarship applicants accepted training scholarships. UNR Integration 7 fellowships. Nevada Primary Care 11 Scholarships, 13 PCP’s, 3 MA learners, 7 EKG learners. High Sierra AHEC 15 scholarships for Spring 2026 semester. Total of 39 applications were received for Spring 2026. UNR CASAT Supervision: 10 new licensed PRSS-S; 1 new licensed ADG Supervisors. UNLV BeHere 23 scholarship recipients. UNR Resilience 12 - Public Health Certificates 9- Full time online MPH program. | 0
406 | DPBH | 23IBCLC02 | DHHS-DPBH | N/A | International Board Certified Lactation Consultants | 2023-06-15 | 2026-12-31 | 3234 | 21 | 666000 |  | 0 | 666000 | [6 empty] | 0 | 666000 |  |  |  | 4997.96 | 157255.49 | 146102 |  | 308355.45 | 357644.55 | 46.3% | 0 | 35764.46 | 35764.46 | 35764.46 | 35764.46 | 35764.46 | 35764.46 | 35764.46 | 35764.46 | 35764.46 | 35764.41 | 0 | 357644.55 | 0 | On Track | Final 6 of Level 3 scholarships were distributed. Level 1 and level 2 program began with a total of 52 scholarship recipients. Out of those, 16 people completed their certifications and two are completing their certification requirements. | 0
406 | DPBH | 23LCCMS01 | DHHS-DPBH | N/A | Lakes Crossing Camera System | 2022-08-18 | 2026-04-30 | 3645 | 61 | 1462644 |  |  | 1462644 |  |  |  |  | 288337.5 |  | 288337.5 | 1174306.5 |  |  | 24377.24 | 103040.13 | 888600.13 | 106331.97 |  | 1122349.47 | 51957.03 | 95.58% | 0 | 2026-03-15: 25978.52; 2026-04-14: 25978.51 | 0 | 51957.03 | 0 | On Track | Project performance period extended for continued work and support of completing project tasks. An upgrade to the flooring in the area this project took place is going to occur. Contract with flooring vendor in process. $288,337.50 to 24JBMHP01 through de-obligation completed. Remaining balance expected to be exhausted by end of project period. | 0
406 | DPBH | 23LRHA01 | DHHS-DPBH | N/A | Local & Regional Authorities Washoe, Carson, Churchill & SNHD (Merged) | 2022-08-17 | 2026-12-31 | 3234 | 23 | 20800000 |  |  | 20800000 | [6 empty] | 0 | 20800000 |  |  | 4661930.94 | 2517080.94 | 3263651.78 | 5221363.1 | 0 | 15664026.76 | 5135973.24 | 75.31% | 0 | 513597.32 | 513597.32 | 513597.32 | 513597.32 | 513597.32 | 513597.32 | 513597.32 | 513597.32 | 513597.32 | 513597.36 | 0 | 5135973.24 | 0 | On Track | Washoe: The project is on time and on budget. A lot has been accomplished. Furniture has been delivered and cubicles installed. The cabinetry is complete and punch list items are starting to be worked through. The project is scheduled for early March CofO and a ribbon cutting on March 26th. Carson: The project is on track to fully expend, which support staffing of key positions within the agency. Churchill: In progress. Equipment was purchased in January 2026, 25% of the Security Equipment ordered for CNHD. All but two pieces of equipment have been relocated. | 0
406 | DPBH | 23NBSTR01 | DHHS-DPBH | N/A | UNR NSPHL Newborn | 2022-10-20 | 2026-10-31 | 3222 | 33 | 3953689 |  |  | 3953689 | [6 empty] | 0 | 3953689 |  |  |  | 820927.41 | 1889733.67 | 570544.16 |  | 3281205.24 | 672483.76 | 82.99% | 0 | 432500.87 | 34283.27 | 34283.27 | 34283.27 | 34283.27 | 34283.27 | 34283.27 | 34283.27 |  |  | 0 | 672483.76 | 0 | On Track | Spend down is on track; 3 of the 5 remaining disorders will be added to the panel after the building certificate of occupancy is granted in October 2026 as equipment can't be set up until they are in the new building. NSPHL states they will completely spend down and have a year to expend the final 18% of the award remaining. | 0
406 | DPBH | 23RCCLV01 | DHHS-DPBH | N/A | RECUPERATIVE CARE CENTER EXPANSION | 2022-10-20 | 2026-09-30 | 3161 | 63 | 10000000 |  |  | 10000000 | [6 empty] | 0 | 10000000 |  |  |  | 0 | 1648607.93 | 4865404.17 |  | 6514012.1 | 3485987.9 | 65.14% | 0 | 1592401.41 | 315597.75 | 315597.75 | 315597.75 | 315597.75 | 315597.75 | 315597.74 |  |  |  | 0 | 3485987.9 | 0 | On Track | Project is ongoing and has incurred $7,790,814.24 in expenditures as of March 15th, 2026. Expected to fully spend down by end of project period. | 0
406 | DPBH | 23RHSCC01 | DHHS-DPBH | N/A | Reproductive Health Services | 2023-01-01 | 2026-12-31 | 3224 | 01, 15 | 6446148 |  |  | 6446148 | [6 empty] | 0 | 6446148 |  |  | 105015.49 | 1191335.83 | 1489526.75 | 555279.31 |  | 3341157.38 | 3104990.62 | 51.83% | 0 | 310499.06 | 310499.06 | 310499.06 | 310499.06 | 310499.06 | 310499.06 | 310499.06 | 310499.06 | 310499.06 | 310499.08 | 0 | 3104990.62 | 0 | On Track | ARPA funding supports subgrants to three other reproductive health service programs, Carson City Health and Human Services (CCHHS), Central Nevada Health District (CNHD), and Northern Nevada Public Health (NNPH). All three subgrantees have submitted spend plans for the entirety of the project period; spend plans submitted are based by SFY, hence the projections have been broken out monthly based on subrecipients projections. Spend plans ascertain they will fully expend their award amounts by the end of the project period, December 31, 2026. Additionally, ARPA is being highly depended on during these unknowing moments for CHN and the sub awardees as it still remains unclear as to whether Title X will continue to fully fund programs, although Title X has released the second NOGAs for this project year (from April 1, 2025 – March 31, 2026). | 0
406 | DPBH | 24FPROS01 | DHHS-DPBH | N/A | Forensic Professional Services - Lake Crossing | 2023-12-13 | 2026-12-31 | 3645 | 62 | 4920000 |  |  | 4920000 | 660000 |  | 744094 |  |  |  | 1404094 | 3515906 |  |  |  | 127478.69 | 1251293.04 | 883052.75 |  | 2261824.48 | 1254081.52 | 64.33% | 0 | 163371.49 | 121190 | 121190 | 121190 | 121190 | 121190 | 121190 | 121190 | 121190 | 121190.03 | 0 | 1254081.52 | 0 | On Track | Contracted clinical staff continue to serve the program in way of evaluations and competency based services. The projections are based on the same number of contractors working the same number of hours each week. Program leadership and fiscal management work closely together to ensure allocation is utilized entirely within the performance period. | 0
406 | DPBH | 24JBMHP01 | DHHS-DPBH | N/A | Forensic Jail Based Mental Health Programs (SNAMHS/NNAMHS) | 2023-12-13 | 2026-12-31 | 3161 | 64 | 14905281 | 3691097.1 |  | 18596378.1 | [6 empty] | 0 | 18596378.1 |  |  |  | 375456.73 | 9082223.3 | 3879806.13 |  | 13337486.16 | 5258891.94 | 71.72% | 0 | 817546.13 | 493482.87 | 493482.87 | 493482.87 | 493482.87 | 493482.87 | 493482.87 | 493482.87 | 493482.87 | 493482.85 | 0 | 5258891.94 | 0 | On Track | Sub-awards have been executed and awarded to Clark County Detention Center and Washoe County Jail. Program in full operating for Washoe and Clark Counties. Program continues to be the destination of re-allocated funds to support ongoing efforts. | 0
406 | DPBH | 24SNFLT01 | DHHS-DPBH | N/A | Skilled Nursing Facility - Forensic Long-Term Care | 2023-11-17 | 2026-12-31 | 3161 | 65 | 5716150 |  |  | 5716150 |  |  | 593974 | 2721280 |  |  | 3315254 | 2400896 |  |  |  | 192214.88 | 644083.94 | 416920.78 |  | 1253219.6 | 1147676.4 | 52.2% | 0 | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 0 | 1147676.4 | 0 | On Track | Remaining funds are expected to be fully expended, in equal parts for remaining months of project period. | 0
407 | DWSS | 23ACNVM01 | DHHS-DSS | N/A | ACCESS NEVADA MODERNIZATION No Wrong Door Single Web Portal | 2022-10-25 | 2026-12-31 | 3228 | 53 | 3112296 |  | 9387704 | 12500000 | [6 empty] | 0 | 12500000 |  |  |  | 4148997.17 | 3964544.82 | 1113910.94 |  | 9227452.93 | 3272547.07 | 73.82% | 0 | 2026-03-15: 25576.1; 2026-04-14: 1217561.97; 2026-05-14: 1064202; 2026-06-13: 965207 | 0 | 3272547.07 | 0 | ON-TRACK | Projections are based on monthly deliverables and remaining GTO billings through June 2026. | 0
407 | DWSS | 23CHDIF01 | DHHS-DSS | N/A | CHILD CARE INFRASTRUCTURE | 2022-05-06 | 2026-12-31 | 3267 | 55 | 30000000 |  |  | 30000000 | [6 empty] | 0 | 30000000 |  |  | 8455742.56 | 11363038.52 | 5323464.92 | 3510010.03 |  | 28652256.03 | 1347743.97 | 95.51% | 0 | 334641.14 | 81256.84 | 869758.75 | 6256.84 | 6256.84 | 10008.64 | 9757.79 | 9509.36 | 12756.84 | 7540.93 | 0 | 1347743.97 | 0 | ON-TRACK | All projects are monitored monthly and spending remains on track. | 0
407 | DSS | 23NOMAD01 | DHHS-DSS | N/A | NOMADS MODERNIZATION | 2022-10-20 | 2026-12-31 | 3228 | 64 | 48510328 |  |  | 48510328 | [6 empty] | 0 | 48510328 |  |  | 2963017.72 | 6787741.04 | 10541855.11 | 7837260.53 |  | 28129874.4 | 20380453.6 | 57.99% | 0 | 2650824.4 | 3250651 | 2967120 | 3013235 | 1207952 | 1934308.45 | 1212286 | 1235001 | 1235001 | 1674074.75 | 0 | 20380453.6 | 0 | ON-TRACK | Projections are based on contractual/MSA deliverables, a pending licensing purchase and a pending equipment purchase. | 0
407 | DSS | 24SUEBT01 | DHHS-DSS |  | DWSS Summer EBT | 2024-06-13 | 2025-12-31 | 3228 | 49 | 6239322 |  |  | 6239322 | [6 empty] | 0 | 6239322 |  |  |  |  | 5209115.23 | 857346.95 |  | 6066462.18 | 172859.82 | 97.23% | 0 | 2026-03-15: 102675.49; 2026-04-14: 70184.33 | 0 | 172859.82 | 6.4028e-10 | ON-TRACK | A final JV to cover SEBT cost-allocated payroll in 3233 is the last item needed to close out this project. | 0
409 | DCFS | 22DSWHD01 | DHHS-DCFS-SNCAS | N/A | DESERT WILLOW HARDENING CIP#: 22-A012 Ceiling Replacement | 2022-04-07 | 2026-12-31 | 3646 | 48 | 916718 |  |  | 916718 | [6 empty] | 0 | 916718 |  | 422.52 | 71653.31 | 139935.27 | 244571.99 | 9720 |  | 466303.09 | 450414.91 | 50.87% | 0 | 49800 | 49800 | 49800 | 48900 | 48900 | 48900 | 48900 | 48900 | 48900 | 7614.91 | 0 | 450414.91 | 0 | On-Track | Spending plan provided by SPWD for Ceiling Replacement Project 22DSWD01 (Project #22-A012) which is estimated to be completed by December 2026. The Unit Hardening project will be contracted to Whiting Turner and is scheduled to begin in April 2026 and be complete December 2026. Per SPWD, $49,800 a month is expected to be expended through the end of the project. | 0
409 | DCFS | 22DSWHD01a | DHHS-DCFS-SNCAS | N/A | DESERT WILLOW HARDENING CIP Project#: 23-A005 Anti-Ligature & Unit Hardening | 2022-08-18 | 2026-12-31 | 3646 | 49 | 5072061 |  |  | 5072061 | [6 empty] | 0 | 5072061 |  |  | 155077.8 | 1178187.53 | 1203299.41 | 932163.46 |  | 3468728.2 | 1603332.8 | 68.39% | 0 | 180100 | 180100 | 180100 | 180100 | 180100 | 180100 | 180100 | 180100 | 162532.8 | 0 | 0 | 1603332.8 | 0 | On-Track | Spending plan provided by SPWD for 22DSWD01a (Project #23-A005) which is estimated to be completed by December 2026. The Unit Hardening project will be contracted to Whiting Turner and is scheduled to begin in April 2026 and be complete December 2026. Funding for this work is supplemented by CIP project 23-M02 as an emergent need, however we plan to spend ARPA funds first which is why the projection shows 23-A005 spending mostly complete by August 2026. Per SPWD, $180,100 a month is expected to be expended through the end of the project. | 0
409 | DCFS | 23CLKCW01 | DHHS-DCFS | N/A | CLARK COUNTY CHILD WELFARE | 2022-08-18 | 2026-06-30 | 3145 | 44 | 4198804 |  |  | 4198804 | [6 empty] | 0 | 4198804 |  |  |  | 769154.54 | 106694 | 843944.5 |  | 1719793.04 | 2479010.96 | 40.96% | 0 | 2026-03-15: 600000; 2026-04-14: 600000; 2026-05-14: 600000; 2026-06-13: 679010.96 |  | 2479010.96 | 0 | Delays | This project allocates ARPA funds to develop the new Clark County Clinical and Community Services (CCS) department. The new department represents a major system transformation for Clark County, establishing a dedicated division to support the implementation of Family First Prevention Services Act (FFPSA), Differential Response, and enhanced Medicaid-funded services for children with behavioral health needs. This plan aligns expenditures with operational readiness and contract execution timelines. Spending between January 2026 – June 2026 emphasizes infrastructure, IT systems, services restructure and hiring staff and training investments required to launch and sustain the department. The County anticipates full drawdown of the $3.3 million by June 30, 2026. Clark County is utilizing this ARPA project to set up a Qualified Residential Treatment Program (QRTP) which provides non-foster family home setting that is intended for children and youth with behavioral health challenges. Projections from February through June 2026 are based on current spending trends. | 0
409 | DCFS | 23EMGCS02 | DHHS-DCFS | N/A | EMERGENCY FUNDING FOR CHILD AND FAMILY SERVICES | 2023-01-31 | 2026-06-30 | 3145 | 52 | 5000000 |  |  | 5000000 | [6 empty] | 0 | 5000000 |  |  | 68238.71 | 1386373.2 | 2608138.27 | 48000 | 0 | 4110750.18 | 889249.82 | 82.22% | 0 | 2026-03-15: 378459.48; 2026-04-14: 170265; 2026-05-14: 170265; 2026-06-13: 170260.34 |  | 889249.82 | 0 | On target | Projections based on the adjusted monthly flat fee of the Magellan contract of $200,000 a month from November 2025 to March 2026 and $187,000 a month from April 2026 to December 2026. Distribution and allocation of the remaining funds is based on the remaining balance in each project. The March projection includes the expenses from November through March 2026. | 0
409 | DCFS | 23EMPLR02 | DHHS-DCFS | N/A | EMERGENCY AND PLANNED RESPITE | 2022-08-18 | 2026-12-31 | 3146-FY24 | 01 50 | 1461385 |  |  | 1461385 | [6 empty] | 0 | 1461385 |  |  |  | 457171.37 | 834673.11 | 144000 |  | 1435844.48 | 25540.52 | 98.25% | 0 | 25540.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25540.52 | 0 | On target | Projections based on the adjusted monthly flat fee of the Magellan contract of $200,000 a month for November 2025. The remaining funds on this project have been paid in March 2026 for November 2025's invoice. This project is fully expended and remaining servives will be reallocated between the remaining 3 projects. . | 0
409 | DCFS | 23FTFPS01 | DHHS-DCFS | N/A | FAMILY TO PEER SUPPORT | 2022-08-18 | 2026-12-31 | 3145 3146-FY24 | 42 | 977346 |  | 980629 | 1957975 |  |  | 49755 |  |  |  | 49755 | 1908220 |  |  | 113037.71 | 618345.64 | 719912.25 | 344592.75 |  | 1795888.35 | 112331.65 | 94.11% | 0 | 50000 | 50000 | 12331.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112331.65 | 0 | On target | This project funds NV PEP, Inc to provide Family Peer to Peer Support Services to children with sever emotional disabilities and their families. This project is projected to be fully expended by May 2026. The amounts projected each month are based on current spending trends. | 0
409 | DCFS | 23IFIHS01 | DHHS-DCFS | N/A | INTENSIVE FAMILY IN HOME SERVICES | 2022-10-20 | 2026-12-31 | 3145 3146-FY24 | 01 41 | 2431165 | 91031 | 2474401 | 4996597 |  |  | 120062 | 1250000 |  |  | 1370062 | 3626535 |  |  | 0 | 825501.65 | 1483975.81 | 252000 |  | 2561477.46 | 1065057.54 | 70.63% | 0 | 218000 | 1868 | 11868 | 11868 | 135366 | 136000 | 136000 | 136000 | 136000 | 136000 | 0 | 1058970 | -6087.54 | Savings Identified | Projections based on the adjusted monthly flat fee of the Magellan contract of $200,000 a month from November 2025 to March 2026 and $187,000 a month from April 2026 to December 2026. Distribution and allocation of the remaining funds is based on the remaining balance in each project. The March projection includes the expenses from November through March 2026. | 0
409 | DCFS | 23LVSRC01 | DHHS-DCFS | N/A | VEGAS STRONG RESILIENCY CENTER | 2022-12-15 | 2026-06-30 | 3145 | 68 | 7022777 |  |  | 7022777 |  | 401607 |  |  |  |  | 401607 | 6621170 |  |  | 0 | 196177.75 | 644440 | 4846108.36 |  | 5686726.11 | 934443.89 | 85.89% | 0 | 2026-03-15: 233611; 2026-04-14: 233611; 2026-05-14: 233611; 2026-06-13: 233610.89 |  | 934443.89 | 0 | On target | This construction project has multiple funding sources that have varying deadlines for funds to be expended: ARPA funds of $6.5m from DCFS and $2m from GFO – these funds are available until 12/31/26 and are anticipated to be fully expended by June 2026– these amounts are projected and will vary from month to month based on work completed and invoiced by vendors. | 0
409 | DCFS | 23NWFEO01 | DHHS-DCFS | N/A | Nursing Workforce Educational Opportunity | 2022-10-20 | 2026-09-30 | 3145 | 66 | 6000000 |  |  | 6000000 | 0 | [5 empty] | 0 | 6000000 |  |  | 1189702.67 | 2364177.05 | 390185.8 | 1677521.33 |  | 5508086.32 | 491913.68 | 91.8% | 0 | 196166 | 0 | 0 | 105000 | 0 | 0 | 190747.68 |  |  |  |  | 491913.68 | -6.4028e-10 | On target | DCFS staff are in contact with UNR's grant staff to ensure billing is up to date. Currently, UNR has the current cohort of 46 students enrolled for Spring 26, 32 students for Summer 2026 and 30 students for Fall 2026. In addition, UNR will be awarding scholarships to 40-60 additional students between Fall 2025-Fall 2026 semesters. Projections are based on scholarship support for APRN students by semester. | 0
409 | DCFS | 23SUPST3145 | DHHS-DCFS | N/A | ARPA OVERSIGHT (8 FTE Support Positions) | 2024-07-01 | 2027-02-28 | 3145 | 01, 43 | 1014987 |  | 232771 | 1247758 |  |  |  |  | 200000 |  | 200000 | 1047758 |  |  |  |  | 938792.53 | 55686.02 |  | 994478.55 | 53279.45 | 94.91% | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 3279.45 | 0 | 0 | 0 | 0 | 0 | 53279.45 | 0 | On target | This project oversees ARPA projects to provide support in the areas of fiscal, reporting, subrecipient monitoring, grants management, contract management and human resources to comply with federal and state regulations. The amounts projected each month are based on current spending trends for 1 temp contractor | 0
409 | DCFS | 23SUPST3146 | DHHS-DCFS | N/A | CHILDRENS BEHAVIORAL HEALTH AUTHORITY (8 FTE Support Positions) | 2024-07-01 | 2027-02-28 | 3146 | 01, 43 | 1499500 |  |  | 1499500 |  |  |  | 232771 |  |  | 232771 | 1266729 |  |  |  |  | 1041847.17 | 169578.59 |  | 1211425.76 | 55303.24 | 95.63% | 0 | 20000 | 20000 | 15303.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55303.24 | 0 | On target | This project supports contractors to provide children's behavioral health support for the division. The amounts projected each month are based on current spending trend for 1 temp contractor | 0
409 | DCFS | 23UNITY01 | DHHS-DCFS | N/A | UNITY Replacement | 2022-10-21 | 2026-12-31 | 3143 | 41 | 18370000 |  |  | 18370000 | [6 empty] | 0 | 18370000 |  |  | 8554.95 | 134739.35 | 1523983.62 | 85110 |  | 1752387.92 | 16617612.08 | 9.539% | 0 | 0 | 1846401 | 1846401 | 1846401 | 1846401 | 1846401 | 1846401 | 1846401 | 1846401 | 1846404.08 | 0 | 16617612.08 | 0 | Delays | The agency has communicated with several vendors to identify options that will allow the agency to spend down ARPA funds before December 31, 2026. Two vendors have provided viable options that will expend the funds in time while appearing to resolve the concern expressed by the Children’s Bureau on the initial contract that did not receive approval. While DCFS has not received formal approval, the agency has been working very closely with the Children’s Bureau to ensure the options are viable. Projections based on anticipated costs. | 0
409 | DCFS | 23WINIC01 | DHHS-DCFS | N/A | Wraparound Authority/ intensive Care Coordination | 2022-08-18 | 2026-12-31 | 3145-FY23, 3146-FY24 | 01, 40 | 7314984 |  | 7335048 | 14650032 |  |  |  | 6250348 |  |  | 6250348 | 8399684 |  |  |  | 2545174.34 | 4389270 | 756000 |  | 7690444.34 | 709239.66 | 91.56% | 0 | 378000 | 14867 | 4867 | 4871.66 | 51634 | 51000 | 51000 | 51000 | 51000 | 51000 | 0 | 709239.66 | 0 | On target | Projections based on the adjusted monthly flat fee of the Magellan contract of $200,000 a month from November 2025 to March 2026 and $187,000 a month from April 2026 to December 2026. Distribution and allocation of the remaining funds is based on the remaining balance in each project. The March projection includes the expenses from November through March 2026. | 0
409 | DCFS | 24CMH9A01 | DHHS-DCFS |  | CAMPUS FOR HOPE (formerly DCFS Bldg. 9 renovations - West Charleston Children's Mental Health) | 2024-06-13 | 2026-12-31 | 3646 | 41 | 3888162 | 800000 |  | 4688162 | [6 empty] | 0 | 4688162 |  |  |  |  | 83600 | 2107.84 |  | 85707.84 | 4602454.16 | 1.828% | 0 | 460245 | 460245 | 460245 | 460245 | 460245 | 460245 | 460245 | 460245 | 460245 | 460249.16 | 0 | 4602454.16 | 0 | Delays | This project will build buildings on the Campus for Hope for behavioral health services. The timeline for this project is still being worked on in the contract. The total project is $17.5M of which the ARPA funds will be used first to pay. Projections are based on the total amount of this ARPA project being evenly distributed across the performance period. | 0
[10 empty] | 316608359 | 4987001.1 | 20410553 | 342005913.1 | 660000 | 5401607 | 13026445 | 10467738.4 | 2186587.5 | 0 | 31742377.9 | 310263535.2 | 0 | 422.52 | 18904363.18 | 61698969.45 | 83046929.76 | 51621698.66 | 0 | 215158883.04 | 95104652.16 |  | 0 | 13944929.59 | 12143946.23 | 12354257.26 | 11579588.81 | 7900810.75 | 8377144.45 | 7803159.2 | 7072997.52 | 6889391.93 | 7032102.19 | 0.01 | 95098327.94 | -6324.22
[9 empty] | ck |  |  |  | 0 | [6 empty] | 0 | 0 | [7 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | 1530.07 | 133524.63 | 116176.99 | 251231.69
[24 empty] | 115208.74 | 143709.11 | 260447.92
9216.23

## DHHS-DO
[10 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 620663.74 | 7583393.67 | 2526979.11 | 2966485.78 | 0 | 13697522.3
[29 empty] | RFR'S RECEIVED THROUGH 3/16/2026 |  |  | SPEND PLAN UPDATES - FOR THE REMAINDER OF THE PROJECT PERIOD
Agency Number | Agency | Allocation Number | Recipient Name | Sub Recipient | Project Description | Start Date | End Date | BA# | CAT(s) | Original NOA Amount | Supplemental Allocations NOA Amount | Amendment(s) | TOTAL REVISED ALLOCATION Original NOA + Supplemental + Amendments | SFY 22 Deobligations | SFY 23 Deobligations | SFY 24 Deobligations | SFY 25 Deobligations | SFY 26 Deobligations | SFY 27 Deobligations | Total Deobligations (CALCULATED COLUMN) | TOTAL ALLOCATION (CALCULATED COLUMN) | SFY21 Amount Spent | SFY22 Amount Spent | SFY23 Amount Spent | SFY24 Amount Spent | SFY25 Amount Spent | SFY26 Amount Spent | SFY27 Amount Spent | TOTAL REIMBURSEMENTS PAID PER RFR'S RECEIVED BY SUBRECIPIENTS | TOTAL UNSPENT BALANCE GFO PAYMENT LEDGERS | % Spent | PENDING RFR'S SUBMITTED AFTER 3/16/2026 FOR JULY-FEB | 2026-03-15 | 2026-04-14 | 2026-05-14 | 2026-06-13 | 2026-07-13 | 2026-08-12 | 2026-09-11 | 2026-10-11 | 2026-11-10 | 2026-12-10 | FINAL CLOSE-OUT | SPEND PLAN TOTAL | CK TOTALS (SPEND PLAN TOTAL CANNOT EXCEED UNSPENT BALANCE) | STATUS: *ON-TRACK *DELAYS (explain) *SAVINGS IDENTIFIED ** NO RESPONSE | SUB-RECIPIENT COMMENTS:
400 | DHHS | 23NVTRI01 | DHHS- DO | N/A | NEVADA TRANSPLANT INSTITUTE | 2022-10-20 | 2026-12-31 | 3195 | 39 | 15000000 |  |  | 15000000 | [6 empty] | 0 | 15000000 |  |  | 620663.74 | 7583393.67 | 2526979.11 | 2966485.78 |  | 13697522.3 | 1302477.7 | 91.32% |  | 737095.7 | 107717 | 107717 | 97717 | 97717 | 88063 | 66451 |  |  |  |  | 1302477.7 | 0 | ON-TRACK | - Preliminary site monitor was conducted on 3/5/2026. All infrastructure was observed related to the transplant ecosystem. -Donor Care Unit is expected to open April 15th. All equipment has been purchased and will be delivered once space finishings have been completed. - The Donor Transplant Testing facility is now complete and testing donors in NV. The lab is fully operational and has been surveyed by both FDA and CLIA.
[10 empty] | 15000000 | 0 | 0 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 0 | 0 | 620663.74 | 7583393.67 | 2526979.11 | 2966485.78 | 0 | 13697522.3 | 1302477.7 |  | 0 | 737095.7 | 107717 | 107717 | 97717 | 97717 | 88063 | 66451 | 0 | 0 | 0 | 0 | 1302477.7 | 0
[23 empty] | 1530.07 | 133524.63 | 116176.99 | 251231.69
[24 empty] | 115208.74 | 143709.11 | 260447.92
9216.23

## ADSD
[10 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 55865 | 2104186.89 | 10508411.99 | 5038063.77 | 0 | 17706527.65
[29 empty] | RFR'S RECEIVED THROUGH 3/16/2026 |  |  | SPEND PLAN UPDATES - FOR THE REMAINDER OF THE PROJECT PERIOD
Agency Number | Agency | Allocation Number | Recipient Name | Sub Recipient | Project Description | Start Date | End Date | BA# | CAT(s) | Original NOA Amount | Supplemental Allocations NOA Amount | Amendment(s) | TOTAL REVISED ALLOCATION Original NOA + Supplemental + Amendments | SFY 22 Deobligations | SFY 23 Deobligations | SFY 24 Deobligations | SFY 25 Deobligations | SFY 26 Deobligations | SFY 27 Deobligations | Total Deobligations (CALCULATED COLUMN) | TOTAL ALLOCATION (CALCULATED COLUMN) | SFY21 Amount Spent | SFY22 Amount Spent | SFY23 Amount Spent | SFY24 Amount Spent | SFY25 Amount Spent | SFY26 Amount Spent | SFY27 Amount Spent | TOTAL REIMBURSEMENTS PAID PER RFR'S RECEIVED BY SUBRECIPIENTS | TOTAL UNSPENT BALANCE GFO PAYMENT LEDGERS | % Spent | PENDING RFR'S SUBMITTED AFTER 3/16/2026 FOR JULY-FEB | 2026-03-15 | 2026-04-14 | 2026-05-14 | 2026-06-13 | 2026-07-13 | 2026-08-12 | 2026-09-11 | 2026-10-11 | 2026-11-10 | 2026-12-10 | FINAL CLOSE-OUT | SPEND PLAN TOTAL | CK TOTALS (SPEND PLAN TOTAL CANNOT EXCEED UNSPENT BALANCE) | STATUS: *ON-TRACK *DELAYS (explain) *SAVINGS IDENTIFIED ** NO RESPONSE | SUB-RECIPIENT COMMENTS:
400 | DHHS | 23EIPRC01 | DHHS- DO | N/A | EARLY INTERVENTION PERSONNEL CENTER | 2022-10-20 | 2026-06-30 | 3276 | 40 | 368100 |  |  | 368100 |  |  |  | 13339.4 |  |  | 13339.4 | 354760.6 |  |  | 16749.46 | 69421.2 | 155690.7 | 70607.26 |  | 312468.62 | 42291.98 | 88.08% | 0 | 2026-03-15: 14722.69; 2026-04-14: 11394; 2026-05-14: 9115.2; 2026-06-13: 7060.09 |  | 42291.98 | 0 | On track | This project is for BA3276, which moved to agency 402. Temporary contractor thorugh Manpower, Business Productivity Suite, and educational materials. The contractor will be compensated using the remaining project funds until those funds are fully exhausted.
402 | ADSD | 23CMSMI01 | DHHS-ADSD | N/A | Case Management System Modernization/Integration | 2024-02-08 | 2026-06-30 | 3151 | 41 | 7500000 |  |  | 7500000 | [6 empty] | 0 | 7500000 |  |  | 55865 | 367393.98 | 3197831.07 | 1625153.22 |  | 5246243.27 | 2253756.73 | 69.95% | 0 | 239747.5 | 239747.5 | 249747.5 | 249747.5 | 487147.5 | 249747.5 | 232179.33 | 220347.5 | 85344.9 |  |  | 2253756.73 | 0 | On track | Note that the end date in this file was incorrect. NOA says 12/31/2026. Projection methodology: - Guidesoft Inc MSA Contractors based on monthly average through August 2026, with reduced hours for Sept.-Nov. 2026. - O365 based on monthly average costs. - Insight Public Sector based on contract deliverables. - Wellsky based on contract deliverables.
402 | ADSD | 23FCWPL01 | DHHS-ADSD | N/A | Personal Care Workforce Impact | 2022-10-20 | 2026-12-31 | 3278 | 62 | 5000000 |  |  | 5000000 | 0 |  | 2000000 |  |  |  | 2000000 | 3000000 |  |  |  | 5084.56 | 360844.62 | 378689.99 |  | 744619.17 | 2255380.83 | 24.82% |  | 510745.71 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 82000 | 82000 | 80635.12 |  | 2255380.83 | 0 | On track | Projection methodology: - Public Health Supportive based on project plan. - KPS3 based on project deliverable schedule.
402 | ADSD | 23HCAPD01 | DHHS-ADSD | N/A | Home/Chore Assistance for people with Disabilities | 2022-10-20 | 2026-06-30 | 3278 | 62 | 1559280 |  |  | 1559280 | 0 |  | 59280 |  |  |  | 59280 | 1500000 |  |  |  | 193311.08 | 916278.09 | 135118.2 |  | 1244707.37 | 255292.63 | 82.98% |  | 2026-03-15: 62000; 2026-04-14: 65000; 2026-05-14: 65000; 2026-06-13: 63292.63 |  | 255292.63 | 0 | On track | Projection methodology: - Acumen Fiscal Agent based on monthly projections for self-directed service support (Jan.-Dec. 2025 reflects approved services, monthly average used for Dec. 2025-Jun. 2026) - Washoe County based on projections for direct services, reflects the monthly average used for Dec. 2025-Feb. 2026) - Jewish Family Service Agency based on projections for monthly direct service and administrative cost (amount varies by month)
402 | ADSD | 23INHSV01 | DHHS-ADSD | N/A | In home Services, home modifications, assistive tech | 2022-10-20 | 2026-12-31 | 3278 | 62 | 2090000 |  |  | 2090000 | 0 |  | 59280 |  |  |  | 59280 | 2030720 |  |  |  | 1001269.81 | 942256.53 | 63141.5 |  | 2006667.84 | 24052.16 | 98.82% |  | 2026-03-15: 13559; 2026-04-14: 10493.16 |  | 24052.16 | -1.4916e-10 | On track | Working with subrecipient/provider to fix RFR errors before payment.
402 | ADSD | 23RFPCN01 | DHHS-ADSD | N/A | RFP Consultant for Intensive Behavioral Support Homes | 2022-10-20 | 2026-12-31 | 3279 | 34 | 14520000 |  |  | 14520000 |  |  | 2000000 |  | 1698250 |  | 3698250 | 10821750 |  |  |  | 185103.94 | 1468023.98 | 1998218.27 |  | 3651346.19 | 7170403.81 | 33.74% |  | 717040.38 | 717040.38 | 717040.38 | 717040.38 | 717040.38 | 717040.38 | 717040.38 | 717040.38 | 717040.38 | 717040.39 |  | 7170403.81 | 0 | On track | Based on our current expenditures and the understanding that we will be making additional expenditures due to Incentives being paid out to the participating providers.
402 | ADSD | 23RSBEX01 | DHHS-ADSD | N/A | Residential Setting Beds Expansion | 2022-10-20 | 2026-03-31 | 3278 | 63 | 4000000 |  |  | 4000000 | [6 empty] | 0 | 4000000 |  |  |  | 127023.52 | 3144731.74 | 715680.38 |  | 3987435.64 | 12564.36 | 99.69% |  | 2026-03-15: 12327.68 |  | 12327.68 | -236.68 | Savings Identified | Subaward de-obligations
402 | ADSD | 23SVNEX01 | DHHS-ADSD | N/A | Service Navigation Expansion | 2022-10-20 | 2026-12-31 | 3278 | 62 | 1646881 |  |  | 1646881 | 0 |  | 500000 |  |  |  | 500000 | 1146881 |  |  |  | 225000 | 478445.96 | 122062.21 |  | 825508.17 | 321372.83 | 71.98% |  | 50500 | 50500 | 50500 | 50500 | 20000 | 20000 | 20000 | 20000 | 20000 | 19372.83 |  | 321372.83 | 0 | On track | Projection methodology: - Money Management International based on monthly contract amount. - Jewish Family Service Agency, Lyon County, and Access to Healthcare Network based on remaining balance and award, split across remaining months. - KPS3 based on contract deliverables (Start date for additional deliverable in Jan. 2026, continuing through Jun. 2026.) - Nevada Public Health Foundation based on contract deliverables (Higher amount in Apr. and Jun. 2026, other months in project period at $10k.)
[10 empty] | 36316161 | 0 | 0 | 36684261 | 0 | 0 | 4618560 | 0 | 1698250 | 0 | 6330149.4 | 30354111.6 | 0 | 0 | 55865 | 2104186.89 | 10508411.99 | 5038063.77 | 0 | 18018996.27 | 12335115.33 |  | 0 | 1620642.96 | 1344175.04 | 1341403.08 | 1337640.6 | 1474187.88 | 1236787.88 | 1219219.71 | 1039387.88 | 904385.28 | 817048.34 | 0 | 12334878.65 | -236.68
[23 empty] | 1530.07 | 133524.63 | 116176.99 | 251231.69
[24 empty] | 115208.74 | 143709.11 | 260447.92
9216.23

## DPBH
[10 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 5186059.55 | 19027253.27 | 28603483.92 | 20061480.55 | 0 | 72878277.29
[29 empty] | RFR'S RECEIVED THROUGH 3/16/2026 |  |  | SPEND PLAN UPDATES - FOR THE REMAINDER OF THE PROJECT PERIOD
Agency Number | Agency | Allocation Number | Recipient Name | Sub Recipient | Project Description | Start Date | End Date | BA# | CAT(s) | Original NOA Amount | Supplemental Allocations NOA Amount | Amendment(s) | TOTAL REVISED ALLOCATION Original NOA + Supplemental + Amendments | SFY 22 Deobligations | SFY 23 Deobligations | SFY 24 Deobligations | SFY 25 Deobligations | SFY 26 Deobligations | SFY 27 Deobligations | Total Deobligations (CALCULATED COLUMN) | TOTAL ALLOCATION (CALCULATED COLUMN) | SFY21 Amount Spent | SFY22 Amount Spent | SFY23 Amount Spent | SFY24 Amount Spent | SFY25 Amount Spent | SFY26 Amount Spent | SFY27 Amount Spent | TOTAL REIMBURSEMENTS PAID PER RFR'S RECEIVED BY SUBRECIPIENTS | TOTAL UNSPENT BALANCE GFO PAYMENT LEDGERS | % Spent | PENDING RFR'S SUBMITTED AFTER 3/16/2026 FOR JULY-FEB | 2026-03-15 | 2026-04-14 | 2026-05-14 | 2026-06-13 | 2026-07-13 | 2026-08-12 | 2026-09-11 | 2026-10-11 | 2026-11-10 | 2026-12-10 | FINAL CLOSE-OUT | SPEND PLAN TOTAL | CK TOTALS (SPEND PLAN TOTAL CANNOT EXCEED UNSPENT BALANCE) | STATUS: *ON-TRACK *DELAYS (explain) *SAVINGS IDENTIFIED ** NO RESPONSE | SUB-RECIPIENT COMMENTS:
406 | DPBH | 22BHCGM01 | DHHS-DPBH | N/A | CONTRACT MANAGEMENT SYSTEM | 2022-05-05 | 2026-06-30 | 3223 | 19 | 477606 |  |  | 477606 | [6 empty] | 0 | 477606 |  |  | 326628 | 60282 | 39664.2 | 120 |  | 426694.2 | 50911.8 | 89.34% |  | 2026-03-15: 12727.95; 2026-04-14: 12727.95; 2026-05-14: 12727.95; 2026-06-13: 12727.95 |  | 50911.8 | 0 | On Track | Project performance period extended for continued work and support of completing project tasks. System configuration updates are required for templates and documents. Some updates to functionality as well. Spend plan calculated on equal amounts for remaining months of project.
406 | DPBH | 22BHSTF01b-c | DHHS-DPBH | N/A | DPBH STAFFING for ARPA Reporting-SFY24 & SFY25 | 2023-07-01 | 2027-03-31 | 3223 | 01 / 18 | 552445 | 404873 |  | 957318 | [6 empty] | 0 | 957318 |  |  |  | 249208.08 | 252955.18 | 163824.92 |  | 665988.18 | 291329.82 | 69.57% |  | 29132.98 | 29132.98 | 29132.98 | 29132.98 | 29132.98 | 29132.98 | 29132.98 | 29132.98 | 29132.98 | 29133 |  | 291329.82 | 0 | On Track | Project performance period extended for continued work and support of completing project tasks. Project on-track to fully expend all funds. Spend plan calculated on equal amounts for remaining months of project.
406 | DPBH | 23CFAEP01 | DHHS-DPBH | N/A | EPIDEMIOLOGIST | 2022-10-20 | 2026-12-31 | 3219 | 34 | 5000000 |  |  | 5000000 | [6 empty] | 0 | 5000000 |  |  | 5642.56 | 191705.75 | 1410887.74 | 1002900.16 |  | 2611136.21 | 2388863.79 | 52.22% |  | 334381.57 | 228275.8 | 228275.8 | 228275.8 | 228275.8 | 228275.8 | 228275.8 | 228275.8 | 228275.8 | 228275.82 |  | 2388863.79 | 0 | On Track | UNR PhD (3), MS HAB (5), MPH Epi (3; 1 moved to Grad Special), Grad Special MPH Epi (1), Epidemiology and Biostatistics Certificate (3; 1 moved to Grad Special), Online Public Health Data Management and Analysis Certificate (3), Undergraduate Public Health (2), Graduate Assistant MS HAB (3), Graduate Assistant MPH Epi (7). UNLV Call for Applications closed for Spring 2026. Total Scholarships given in Fall 2025: 41(Undergraduate= 6; Master's= 15; Doctoral=20).
406 | DPBH | 23CSSBC01 | DHHS-DPBH | N/A | CRISIS STABILIZATION CENTER | 2022-07-01 | 2026-06-30 | 3165 | 63 | 20000000 |  |  | 20000000 | 0 | 0 | 5000000 |  |  |  | 5000000 | 15000000 |  |  | 4669.1 | 10780348.58 | 3123414.75 | 0 |  | 13908432.43 | 1091567.57 | 92.72% |  | 2026-03-15: 1091567.56 | 0.01 | 1091567.57 | 0 | On Track | The remaining projected balance processed with the Renown subaward, the enitre remaining balance has been expended. Project open to complete close out activities.
406 | DPBH | 23EMGCS01 | DHHS-DPBH-CRISIS RESPONSE | N/A | EMERGENCY CRISIS CARE (Transfer 5 million to DCFS) | 2022-07-01 | 2026-06-30 | 3165 | 64 | 10000000 |  |  | 10000000 | 0 | 5000000 | 1900000 |  |  |  | 6900000 | 3100000 |  |  | 57796.22 | 2079879 | 698605.6 | 249285.96 |  | 3085566.78 | 14433.22 | 99.53% |  | 2026-03-15: 3608.31; 2026-04-14: 3608.31; 2026-05-14: 3608.31; 2026-06-13: 3608.29 |  | 14433.22 | 2.6193e-10 | On Track | There is remaining balance of $14,433.22. Received extension request approval, providing until 6/30/2026 to expend remaining amount giving a monthly projection of $3,608.31 x 4 Months.
406 | DPBH | 23GIDTR01 | DHHS-DPBH | N/A | GENOMIC INFECTIOUS DISEASE TRACKING | 2022-10-20 | 2026-06-30 | 3219 | 35 | 1500000 |  |  | 1500000 | [6 empty] | 0 | 1500000 |  |  |  | 131435.79 | 943395.25 | 381659.96 |  | 1456491 | 43509 | 97.1% |  | 2026-03-15: 10877.25; 2026-04-14: 10877.25; 2026-05-14: 10877.25; 2026-06-13: 10877.25 |  | 43509 | 0 | On Track | Project on track to fully spend down by end of performance period. Spend plan calculated on equal amounts for remaining months of project.
406 | DPBH | 23HCWSS02 | DHHS-DPBH | N/A | Health Care Workforce Scholarships (Transferred from DHCFP) | 2023-06-14 | 2026-12-31 | 3234 | 22 | 5494300 |  |  | 5494300 | [6 empty] | 0 | 5494300 |  |  |  | 201861.5 | 1819585.17 | 1618885.18 |  | 3640331.85 | 1853968.15 | 66.26% |  | 184829.28 | 185459.88 | 185459.88 | 185459.88 | 185459.88 | 185459.88 | 185459.88 | 185459.88 | 185459.88 | 185459.83 |  | 1853968.15 | 0 | On Track | Healthy Communities Coalition 22 scholarship recipients. 20 CHW I, 2 CHW II certifications. 100% spent down. UNR Larson Institute 20 scholarship recipients CHW, 15 English Doula, 17 Spanish Doula scholarship recipients, 20 scholarship applicants accepted training scholarships. UNR Integration 7 fellowships. Nevada Primary Care 11 Scholarships, 13 PCP’s, 3 MA learners, 7 EKG learners. High Sierra AHEC 15 scholarships for Spring 2026 semester. Total of 39 applications were received for Spring 2026. UNR CASAT Supervision: 10 new licensed PRSS-S; 1 new licensed ADG Supervisors. UNLV BeHere 23 scholarship recipients. UNR Resilience 12 - Public Health Certificates 9- Full time online MPH program.
406 | DPBH | 23IBCLC02 | DHHS-DPBH | N/A | International Board Certified Lactation Consultants | 2023-06-15 | 2026-12-31 | 3234 | 21 | 666000 |  | 0 | 666000 | [6 empty] | 0 | 666000 |  |  |  | 4997.96 | 157255.49 | 146102 |  | 308355.45 | 357644.55 | 46.3% |  | 35764.46 | 35764.46 | 35764.46 | 35764.46 | 35764.46 | 35764.46 | 35764.46 | 35764.46 | 35764.46 | 35764.41 |  | 357644.55 | 0 | On Track | Final 6 of Level 3 scholarships were distributed. Level 1 and level 2 program began with a total of 52 scholarship recipients. Out of those, 16 people completed their certifications and two are completing their certification requirements.
406 | DPBH | 23LCCMS01 | DHHS-DPBH | N/A | Lakes Crossing Camera System | 2022-08-18 | 2026-04-30 | 3645 | 61 | 1462644 |  |  | 1462644 |  |  |  |  | 288337.5 |  | 288337.5 | 1174306.5 |  |  | 24377.24 | 103040.13 | 888600.13 | 106331.97 |  | 1122349.47 | 51957.03 | 95.58% |  | 2026-03-15: 25978.52; 2026-04-14: 25978.51 |  | 51957.03 | 0 | On Track | Project performance period extended for continued work and support of completing project tasks. An upgrade to the flooring in the area this project took place is going to occur. Contract with flooring vendor in process. $288,337.50 to 24JBMHP01 through de-obligation completed. Remaining balance expected to be exhausted by end of project period.
406 | DPBH | 23LRHA01 | DHHS-DPBH | N/A | Local & Regional Authorities Washoe, Carson, Churchill & SNHD (Merged) | 2022-08-17 | 2026-12-31 | 3234 | 23 | 20800000 |  |  | 20800000 | [6 empty] | 0 | 20800000 |  |  | 4661930.94 | 2517080.94 | 3263651.78 | 5221363.1 | 0 | 15664026.76 | 5135973.24 | 75.31% |  | 513597.32 | 513597.32 | 513597.32 | 513597.32 | 513597.32 | 513597.32 | 513597.32 | 513597.32 | 513597.32 | 513597.36 |  | 5135973.24 | 0 | On Track | Washoe: The project is on time and on budget. A lot has been accomplished. Furniture has been delivered and cubicles installed. The cabinetry is complete and punch list items are starting to be worked through. The project is scheduled for early March CofO and a ribbon cutting on March 26th. Carson: The project is on track to fully expend, which support staffing of key positions within the agency. Churchill: In progress. Equipment was purchased in January 2026, 25% of the Security Equipment ordered for CNHD. All but two pieces of equipment have been relocated.
406 | DPBH | 23NBSTR01 | DHHS-DPBH | N/A | UNR NSPHL Newborn | 2022-10-20 | 2026-10-31 | 3222 | 33 | 3953689 |  |  | 3953689 | [6 empty] | 0 | 3953689 |  |  |  | 820927.41 | 1889733.67 | 570544.16 |  | 3281205.24 | 672483.76 | 82.99% |  | 432500.87 | 34283.27 | 34283.27 | 34283.27 | 34283.27 | 34283.27 | 34283.27 | 34283.27 |  |  |  | 672483.76 | 0 | On Track | Spend down is on track; 3 of the 5 remaining disorders will be added to the panel after the building certificate of occupancy is granted in October 2026 as equipment can't be set up until they are in the new building. NSPHL states they will completely spend down and have a year to expend the final 18% of the award remaining.
406 | DPBH | 23RCCLV01 | DHHS-DPBH | N/A | RECUPERATIVE CARE CENTER EXPANSION | 2022-10-20 | 2026-09-30 | 3161 | 63 | 10000000 |  |  | 10000000 | [6 empty] | 0 | 10000000 |  |  |  | 0 | 1648607.93 | 4865404.17 |  | 6514012.1 | 3485987.9 | 65.14% |  | 1592401.41 | 315597.75 | 315597.75 | 315597.75 | 315597.75 | 315597.75 | 315597.74 |  |  |  |  | 3485987.9 | 0 | On Track | Project is ongoing and has incurred $7,790,814.24 in expenditures as of March 15th, 2026. Expected to fully spend down by end of project period.
406 | DPBH | 23RHSCC01 | DHHS-DPBH | N/A | Reproductive Health Services | 2023-01-01 | 2026-12-31 | 3224 | 01, 15 | 6446148 |  |  | 6446148 | [6 empty] | 0 | 6446148 |  |  | 105015.49 | 1191335.83 | 1489526.75 | 555279.31 |  | 3341157.38 | 3104990.62 | 51.83% |  | 310499.06 | 310499.06 | 310499.06 | 310499.06 | 310499.06 | 310499.06 | 310499.06 | 310499.06 | 310499.06 | 310499.08 |  | 3104990.62 | 0 | On Track | ARPA funding supports subgrants to three other reproductive health service programs, Carson City Health and Human Services (CCHHS), Central Nevada Health District (CNHD), and Northern Nevada Public Health (NNPH). All three subgrantees have submitted spend plans for the entirety of the project period; spend plans submitted are based by SFY, hence the projections have been broken out monthly based on subrecipients projections. Spend plans ascertain they will fully expend their award amounts by the end of the project period, December 31, 2026. Additionally, ARPA is being highly depended on during these unknowing moments for CHN and the sub awardees as it still remains unclear as to whether Title X will continue to fully fund programs, although Title X has released the second NOGAs for this project year (from April 1, 2025 – March 31, 2026).
406 | DPBH | 24FPROS01 | DHHS-DPBH | N/A | Forensic Professional Services - Lake Crossing | 2023-12-13 | 2026-12-31 | 3645 | 62 | 4920000 |  |  | 4920000 | 660000 |  | 744094 |  |  |  | 1404094 | 3515906 |  |  |  | 127478.69 | 1251293.04 | 883052.75 |  | 2261824.48 | 1254081.52 | 64.33% |  | 163371.49 | 121190 | 121190 | 121190 | 121190 | 121190 | 121190 | 121190 | 121190 | 121190.03 |  | 1254081.52 | 0 | On Track | Contracted clinical staff continue to serve the program in way of evaluations and competency based services. The projections are based on the same number of contractors working the same number of hours each week. Program leadership and fiscal management work closely together to ensure allocation is utilized entirely within the performance period.
406 | DPBH | 24JBMHP01 | DHHS-DPBH | N/A | Forensic Jail Based Mental Health Programs (SNAMHS/NNAMHS) | 2023-12-13 | 2026-12-31 | 3161 | 64 | 14905281 | 3691097.1 |  | 18596378.1 | [6 empty] | 0 | 18596378.1 |  |  |  | 375456.73 | 9082223.3 | 3879806.13 |  | 13337486.16 | 5258891.94 | 71.72% |  | 817546.13 | 493482.87 | 493482.87 | 493482.87 | 493482.87 | 493482.87 | 493482.87 | 493482.87 | 493482.87 | 493482.85 |  | 5258891.94 | 0 | On Track | Sub-awards have been executed and awarded to Clark County Detention Center and Washoe County Jail. Program in full operating for Washoe and Clark Counties. Program continues to be the destination of re-allocated funds to support ongoing efforts.
406 | DPBH | 24SNFLT01 | DHHS-DPBH | N/A | Skilled Nursing Facility - Forensic Long-Term Care | 2023-11-17 | 2026-12-31 | 3161 | 65 | 5716150 |  |  | 5716150 |  |  | 593974 | 2721280 |  |  | 3315254 | 2400896 |  |  |  | 192214.88 | 644083.94 | 416920.78 |  | 1253219.6 | 1147676.4 | 52.2% |  | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 114767.64 | 114767.64 |  | 1147676.4 | 0 | On Track | Remaining funds are expected to be fully expended, in equal parts for remaining months of project period.
[10 empty] | 111894263 | 4095970.1 | 0 | 115990233.1 | 660000 | 5000000 | 8238068 | 2721280 | 288337.5 | 0 | 16907685.5 | 99082547.6 | 0 | 0 | 5186059.55 | 19027253.27 | 28603483.92 | 20061480.55 | 0 | 72878277.29 | 26204270.31 |  | 0 | 5673551.8 | 2435243.05 | 2409264.54 | 2409264.52 | 2382051.03 | 2382051.03 | 2382051.02 | 2066453.28 | 2032170.01 | 2032170.02 | 0.01 | 26204270.31 | 2.6193e-10
[23 empty] | 1530.07 | 133524.63 | 116176.99 | 251231.69
[24 empty] | 115208.74 | 143709.11 | 260447.92
9216.23

## DSS
[10 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 11418760.28 | 22299776.73 | 25038980.08 | 13318528.45 | 0 | 72076045.54
[29 empty] | RFR'S RECEIVED THROUGH 3/16/2026 |  |  | SPEND PLAN UPDATES - FOR THE REMAINDER OF THE PROJECT PERIOD
Agency Number | Agency | Allocation Number | Recipient Name | Sub Recipient | Project Description | Start Date | End Date | BA# | CAT(s) | Original NOA Amount | Supplemental Allocations NOA Amount | Amendment(s) | TOTAL REVISED ALLOCATION Original NOA + Supplemental + Amendments | SFY 22 Deobligations | SFY 23 Deobligations | SFY 24 Deobligations | SFY 25 Deobligations | SFY 26 Deobligations | SFY 27 Deobligations | Total Deobligations (CALCULATED COLUMN) | TOTAL ALLOCATION (CALCULATED COLUMN) | SFY21 Amount Spent | SFY22 Amount Spent | SFY23 Amount Spent | SFY24 Amount Spent | SFY25 Amount Spent | SFY26 Amount Spent | SFY27 Amount Spent | TOTAL REIMBURSEMENTS PAID PER RFR'S RECEIVED BY SUBRECIPIENTS | TOTAL UNSPENT BALANCE GFO PAYMENT LEDGERS | % Spent | PENDING RFR'S SUBMITTED AFTER 3/16/2026 FOR JULY-FEB | 2026-03-15 | 2026-04-14 | 2026-05-14 | 2026-06-13 | 2026-07-13 | 2026-08-12 | 2026-09-11 | 2026-10-11 | 2026-11-10 | 2026-12-10 | FINAL CLOSE-OUT | SPEND PLAN TOTAL | CK TOTALS (SPEND PLAN TOTAL CANNOT EXCEED UNSPENT BALANCE) | STATUS: *ON-TRACK *DELAYS (explain) *SAVINGS IDENTIFIED ** NO RESPONSE | SUB-RECIPIENT COMMENTS:
407 | DWSS | 23ACNVM01 | DHHS-DSS | N/A | ACCESS NEVADA MODERNIZATION No Wrong Door Single Web Portal | 2022-10-25 | 2026-12-31 | 3228 | 53 | 3112296 |  | 9387704 | 12500000 | [6 empty] | 0 | 12500000 |  |  |  | 4148997.17 | 3964544.82 | 1113910.94 |  | 9227452.93 | 3272547.07 | 73.82% |  | 2026-03-15: 25576.1; 2026-04-14: 1217561.97; 2026-05-14: 1064202; 2026-06-13: 965207 |  | 3272547.07 | 0 | ON-TRACK | Projections are based on monthly deliverables and remaining GTO billings through June 2026.
407 | DWSS | 23CHDIF01 | DHHS-DSS | N/A | CHILD CARE INFRASTRUCTURE | 2022-05-06 | 2026-12-31 | 3267 | 55 | 30000000 |  |  | 30000000 | [6 empty] | 0 | 30000000 |  |  | 8455742.56 | 11363038.52 | 5323464.92 | 3510010.03 |  | 28652256.03 | 1347743.97 | 95.51% |  | 334641.14 | 81256.84 | 869758.75 | 6256.84 | 6256.84 | 10008.64 | 9757.79 | 9509.36 | 12756.84 | 7540.93 |  | 1347743.97 | 0 | ON-TRACK | All projects are monitored monthly and spending remains on track.
407 | DSS | 23NOMAD01 | DHHS-DSS | N/A | NOMADS MODERNIZATION | 2022-10-20 | 2026-12-31 | 3228 | 64 | 48510328 |  |  | 48510328 | [6 empty] | 0 | 48510328 |  |  | 2963017.72 | 6787741.04 | 10541855.11 | 7837260.53 |  | 28129874.4 | 20380453.6 | 57.99% |  | 2650824.4 | 3250651 | 2967120 | 3013235 | 1207952 | 1934308.45 | 1212286 | 1235001 | 1235001 | 1674074.75 |  | 20380453.6 | 0 | ON-TRACK | Projections are based on contractual/MSA deliverables, a pending licensing purchase and a pending equipment purchase.
407 | DSS | 24SUEBT01 | DHHS-DSS |  | DWSS Summer EBT | 2024-06-13 | 2025-12-31 | 3228 | 49 | 6239322 |  |  | 6239322 | [6 empty] | 0 | 6239322 |  |  |  |  | 5209115.23 | 857346.95 |  | 6066462.18 | 172859.82 | 97.23% |  | 2026-03-15: 102675.49; 2026-04-14: 70184.33 |  | 172859.82 | 6.4028e-10 | ON-TRACK | A final JV to cover SEBT cost-allocated payroll in 3233 is the last item needed to close out this project.
[10 empty] | 87861946 | 0 | 9387704 | 97249650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97249650 | 0 | 0 | 11418760.28 | 22299776.73 | 25038980.08 | 13318528.45 | 0 | 72076045.54 | 25173604.46 |  | 0 | 3113717.13 | 4619654.14 | 4901080.75 | 3984698.84 | 1214208.84 | 1944317.09 | 1222043.79 | 1244510.36 | 1247757.84 | 1681615.68 | 0 | 25173604.46 | 6.4028e-10
[23 empty] | 1530.07 | 133524.63 | 116176.99 | 251231.69
[24 empty] | 115208.74 | 143709.11 | 260447.92
9216.23

## DCFS
[10 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 422.52 | 1606265.15 | 10614937.69 | 16213383.96 | 10166532.85 | 0 | 38601542.17
[29 empty] | RFR'S RECEIVED THROUGH 3/16/2026 |  |  | SPEND PLAN UPDATES - FOR THE REMAINDER OF THE PROJECT PERIOD
Agency Number | Agency | Allocation Number | Recipient Name | Sub Recipient | Project Description | Start Date | End Date | BA# | CAT(s) | Original NOA Amount | Supplemental Allocations NOA Amount | Amendment(s) | TOTAL REVISED ALLOCATION Original NOA + Supplemental + Amendments | SFY 22 Deobligations | SFY 23 Deobligations | SFY 24 Deobligations | SFY 25 Deobligations | SFY 26 Deobligations | SFY 27 Deobligations | Total Deobligations (CALCULATED COLUMN) | TOTAL ALLOCATION (CALCULATED COLUMN) | SFY21 Amount Spent | SFY22 Amount Spent | SFY23 Amount Spent | SFY24 Amount Spent | SFY25 Amount Spent | SFY26 Amount Spent | SFY27 Amount Spent | TOTAL REIMBURSEMENTS PAID PER RFR'S RECEIVED BY SUBRECIPIENTS | TOTAL UNSPENT BALANCE GFO PAYMENT LEDGERS | % Spent | PENDING RFR'S SUBMITTED AFTER 3/16/2026 FOR JULY-FEB | 2026-03-15 | 2026-04-14 | 2026-05-14 | 2026-06-13 | 2026-07-13 | 2026-08-12 | 2026-09-11 | 2026-10-11 | 2026-11-10 | 2026-12-10 | FINAL CLOSE-OUT | SPEND PLAN TOTAL | CK TOTALS (SPEND PLAN TOTAL CANNOT EXCEED UNSPENT BALANCE) | STATUS: *ON-TRACK *DELAYS (explain) *SAVINGS IDENTIFIED ** NO RESPONSE | SUB-RECIPIENT COMMENTS:
409 | DCFS | 22DSWHD01 | DHHS-DCFS-SNCAS | N/A | DESERT WILLOW HARDENING CIP#: 22-A012 Ceiling Replacement | 2022-04-07 | 2026-12-31 | 3646 | 48 | 916718 |  |  | 916718 | [6 empty] | 0 | 916718 |  | 422.52 | 71653.31 | 139935.27 | 244571.99 | 9720 |  | 466303.09 | 450414.91 | 50.87% |  | 49800 | 49800 | 49800 | 48900 | 48900 | 48900 | 48900 | 48900 | 48900 | 7614.91 |  | 450414.91 | 0 | On-Track | Spending plan provided by SPWD for Ceiling Replacement Project 22DSWD01 (Project #22-A012) which is estimated to be completed by December 2026. The Unit Hardening project will be contracted to Whiting Turner and is scheduled to begin in April 2026 and be complete December 2026. Per SPWD, $49,800 a month is expected to be expended through the end of the project.
409 | DCFS | 22DSWHD01a | DHHS-DCFS-SNCAS | N/A | DESERT WILLOW HARDENING CIP Project#: 23-A005 Anti-Ligature & Unit Hardening | 2022-08-18 | 2026-12-31 | 3646 | 49 | 5072061 |  |  | 5072061 | [6 empty] | 0 | 5072061 |  |  | 155077.8 | 1178187.53 | 1203299.41 | 932163.46 |  | 3468728.2 | 1603332.8 | 68.39% |  | 180100 | 180100 | 180100 | 180100 | 180100 | 180100 | 180100 | 180100 | 162532.8 |  |  | 1603332.8 | 0 | On-Track | Spending plan provided by SPWD for 22DSWD01a (Project #23-A005) which is estimated to be completed by December 2026. The Unit Hardening project will be contracted to Whiting Turner and is scheduled to begin in April 2026 and be complete December 2026. Funding for this work is supplemented by CIP project 23-M02 as an emergent need, however we plan to spend ARPA funds first which is why the projection shows 23-A005 spending mostly complete by August 2026. Per SPWD, $180,100 a month is expected to be expended through the end of the project.
409 | DCFS | 23CLKCW01 | DHHS-DCFS | N/A | CLARK COUNTY CHILD WELFARE | 2022-08-18 | 2026-06-30 | 3145 | 44 | 4198804 |  |  | 4198804 | [6 empty] | 0 | 4198804 |  |  |  | 769154.54 | 106694 | 843944.5 |  | 1719793.04 | 2479010.96 | 40.96% |  | 2026-03-15: 600000; 2026-04-14: 600000; 2026-05-14: 600000; 2026-06-13: 679010.96 |  | 2479010.96 | 0 | Delays | This project allocates ARPA funds to develop the new Clark County Clinical and Community Services (CCS) department. The new department represents a major system transformation for Clark County, establishing a dedicated division to support the implementation of Family First Prevention Services Act (FFPSA), Differential Response, and enhanced Medicaid-funded services for children with behavioral health needs. This plan aligns expenditures with operational readiness and contract execution timelines. Spending between January 2026 – June 2026 emphasizes infrastructure, IT systems, services restructure and hiring staff and training investments required to launch and sustain the department. The County anticipates full drawdown of the $3.3 million by June 30, 2026. Clark County is utilizing this ARPA project to set up a Qualified Residential Treatment Program (QRTP) which provides non-foster family home setting that is intended for children and youth with behavioral health challenges. Projections from February through June 2026 are based on current spending trends.
409 | DCFS | 23EMGCS02 | DHHS-DCFS | N/A | EMERGENCY FUNDING FOR CHILD AND FAMILY SERVICES | 2023-01-31 | 2026-06-30 | 3145 | 52 | 5000000 |  |  | 5000000 | [6 empty] | 0 | 5000000 |  |  | 68238.71 | 1386373.2 | 2608138.27 | 48000 | 0 | 4110750.18 | 889249.82 | 82.22% |  | 2026-03-15: 378459.48; 2026-04-14: 170265; 2026-05-14: 170265; 2026-06-13: 170260.34 |  | 889249.82 | 0 | On target | Projections based on the adjusted monthly flat fee of the Magellan contract of $200,000 a month from November 2025 to March 2026 and $187,000 a month from April 2026 to December 2026. Distribution and allocation of the remaining funds is based on the remaining balance in each project. The March projection includes the expenses from November through March 2026.
409 | DCFS | 23EMPLR02 | DHHS-DCFS | N/A | EMERGENCY AND PLANNED RESPITE | 2022-08-18 | 2026-12-31 | 3146-FY24 | 01 50 | 1461385 |  |  | 1461385 | [6 empty] | 0 | 1461385 |  |  |  | 457171.37 | 834673.11 | 144000 |  | 1435844.48 | 25540.52 | 98.25% |  | 25540.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25540.52 | 0 | On target | Projections based on the adjusted monthly flat fee of the Magellan contract of $200,000 a month for November 2025. The remaining funds on this project have been paid in March 2026 for November 2025's invoice. This project is fully expended and remaining servives will be reallocated between the remaining 3 projects. .
409 | DCFS | 23FTFPS01 | DHHS-DCFS | N/A | FAMILY TO PEER SUPPORT | 2022-08-18 | 2026-12-31 | 3145 3146-FY24 | 42 | 977346 |  | 980629 | 1957975 |  |  | 49755 |  |  |  | 49755 | 1908220 |  |  | 113037.71 | 618345.64 | 719912.25 | 344592.75 |  | 1795888.35 | 112331.65 | 94.11% |  | 2026-03-15: 50000; 2026-04-14: 50000; 2026-05-14: 12331.65 |  | 112331.65 | 0 | On target | This project funds NV PEP, Inc to provide Family Peer to Peer Support Services to children with sever emotional disabilities and their families. This project is projected to be fully expended by May 2026. The amounts projected each month are based on current spending trends.
409 | DCFS | 23IFIHS01 | DHHS-DCFS | N/A | INTENSIVE FAMILY IN HOME SERVICES | 2022-10-20 | 2026-12-31 | 3145 3146-FY24 | 01 41 | 2431165 | 91031 | 2474401 | 4996597 |  |  | 120062 | 1250000 |  |  | 1370062 | 3626535 |  |  | 0 | 825501.65 | 1483975.81 | 252000 |  | 2561477.46 | 1065057.54 | 70.63% |  | 218000 | 1868 | 11868 | 11868 | 135366 | 136000 | 136000 | 136000 | 136000 | 136000 |  | 1058970 | -6087.54 | Savings Identified | Projections based on the adjusted monthly flat fee of the Magellan contract of $200,000 a month from November 2025 to March 2026 and $187,000 a month from April 2026 to December 2026. Distribution and allocation of the remaining funds is based on the remaining balance in each project. The March projection includes the expenses from November through March 2026.
409 | DCFS | 23LVSRC01 | DHHS-DCFS | N/A | VEGAS STRONG RESILIENCY CENTER | 2022-12-15 | 2026-06-30 | 3145 | 68 | 7022777 |  |  | 7022777 |  | 401607 |  |  |  |  | 401607 | 6621170 |  |  | 0 | 196177.75 | 644440 | 4846108.36 |  | 5686726.11 | 934443.89 | 85.89% |  | 2026-03-15: 233611; 2026-04-14: 233611; 2026-05-14: 233611; 2026-06-13: 233610.89 |  | 934443.89 | 0 | On target | This construction project has multiple funding sources that have varying deadlines for funds to be expended: ARPA funds of $6.5m from DCFS and $2m from GFO – these funds are available until 12/31/26 and are anticipated to be fully expended by June 2026– these amounts are projected and will vary from month to month based on work completed and invoiced by vendors.
409 | DCFS | 23NWFEO01 | DHHS-DCFS | N/A | Nursing Workforce Educational Opportunity | 2022-10-20 | 2026-09-30 | 3145 | 66 | 6000000 |  |  | 6000000 | 0 | [5 empty] | 0 | 6000000 |  |  | 1189702.67 | 2364177.05 | 390185.8 | 1677521.33 |  | 5508086.32 | 491913.68 | 91.8% |  | 196166 | 0 | 0 | 105000 | 0 | 0 | 190747.68 |  |  |  |  | 491913.68 | -6.4028e-10 | On target | DCFS staff are in contact with UNR's grant staff to ensure billing is up to date. Currently, UNR has the current cohort of 46 students enrolled for Spring 26, 32 students for Summer 2026 and 30 students for Fall 2026. In addition, UNR will be awarding scholarships to 40-60 additional students between Fall 2025-Fall 2026 semesters. Projections are based on scholarship support for APRN students by semester.
409 | DCFS | 23SUPST3145 | DHHS-DCFS | N/A | ARPA OVERSIGHT (8 FTE Support Positions) | 2024-07-01 | 2027-02-28 | 3145 | 01, 43 | 1014987 |  | 232771 | 1247758 |  |  |  |  | 200000 |  | 200000 | 1047758 |  |  |  |  | 938792.53 | 55686.02 |  | 994478.55 | 53279.45 | 94.91% |  | 10000 | 10000 | 10000 | 10000 | 10000 | 3279.45 | [5 empty] | 53279.45 | 0 | On target | This project oversees ARPA projects to provide support in the areas of fiscal, reporting, subrecipient monitoring, grants management, contract management and human resources to comply with federal and state regulations. The amounts projected each month are based on current spending trends for 1 temp contractor
409 | DCFS | 23SUPST3146 | DHHS-DCFS | N/A | CHILDRENS BEHAVIORAL HEALTH AUTHORITY (8 FTE Support Positions) | 2024-07-01 | 2027-02-28 | 3146 | 01, 43 | 1499500 |  |  | 1499500 |  |  |  | 232771 |  |  | 232771 | 1266729 |  |  |  |  | 1041847.17 | 169578.59 |  | 1211425.76 | 55303.24 | 95.63% |  | 2026-03-15: 20000; 2026-04-14: 20000; 2026-05-14: 15303.24 |  | 55303.24 | 0 | On target | This project supports contractors to provide children's behavioral health support for the division. The amounts projected each month are based on current spending trend for 1 temp contractor
409 | DCFS | 23UNITY01 | DHHS-DCFS | N/A | UNITY Replacement | 2022-10-21 | 2026-12-31 | 3143 | 41 | 18370000 |  |  | 18370000 | [6 empty] | 0 | 18370000 |  |  | 8554.95 | 134739.35 | 1523983.62 | 85110 |  | 1752387.92 | 16617612.08 | 9.539% |  |  | 1846401 | 1846401 | 1846401 | 1846401 | 1846401 | 1846401 | 1846401 | 1846401 | 1846404.08 |  | 16617612.08 | 0 | Delays | The agency has communicated with several vendors to identify options that will allow the agency to spend down ARPA funds before December 31, 2026. Two vendors have provided viable options that will expend the funds in time while appearing to resolve the concern expressed by the Children’s Bureau on the initial contract that did not receive approval. While DCFS has not received formal approval, the agency has been working very closely with the Children’s Bureau to ensure the options are viable. Projections based on anticipated costs.
409 | DCFS | 23WINIC01 | DHHS-DCFS | N/A | Wraparound Authority/ intensive Care Coordination | 2022-08-18 | 2026-12-31 | 3145-FY23, 3146-FY24 | 01, 40 | 7314984 |  | 7335048 | 14650032 |  |  |  | 6250348 |  |  | 6250348 | 8399684 |  |  |  | 2545174.34 | 4389270 | 756000 |  | 7690444.34 | 709239.66 | 91.56% |  | 378000 | 14867 | 4867 | 4871.66 | 51634 | 51000 | 51000 | 51000 | 51000 | 51000 |  | 709239.66 | 0 | On target | Projections based on the adjusted monthly flat fee of the Magellan contract of $200,000 a month from November 2025 to March 2026 and $187,000 a month from April 2026 to December 2026. Distribution and allocation of the remaining funds is based on the remaining balance in each project. The March projection includes the expenses from November through March 2026.
409 | DCFS | 24CMH9A01 | DHHS-DCFS |  | CAMPUS FOR HOPE (formerly DCFS Bldg. 9 renovations - West Charleston Children's Mental Health) | 2024-06-13 | 2026-12-31 | 3646 | 41 | 3888162 | 800000 |  | 4688162 | [6 empty] | 0 | 4688162 |  |  |  |  | 83600 | 2107.84 |  | 85707.84 | 4602454.16 | 1.828% |  | 460245 | 460245 | 460245 | 460245 | 460245 | 460245 | 460245 | 460245 | 460245 | 460249.16 |  | 4602454.16 | 0 | Delays | This project will build buildings on the Campus for Hope for behavioral health services. The timeline for this project is still being worked on in the contract. The total project is $17.5M of which the ARPA funds will be used first to pay. Projections are based on the total amount of this ARPA project being evenly distributed across the performance period.
[10 empty] | 65167889 | 891031 | 11022849 | 77081769 | 0 | 401607 | 169817 | 7733119 | 200000 | 0 | 8504543 | 68577226 | 0 | 422.52 | 1606265.15 | 10614937.69 | 16213383.96 | 10166532.85 | 0 | 38488041.64 | 30089184.36 |  | 0 | 2799922 | 3637157 | 3594791.89 | 3750267.85 | 2732646 | 2725925.45 | 2913393.68 | 2722646 | 2705078.8 | 2501268.15 | 0 | 30083096.82 | -6087.54
[23 empty] | 1530.07 | 133524.63 | 116176.99 | 251231.69
[24 empty] | 115208.74 | 143709.11 | 260447.92
9216.23